## 142676- Structure Frame
C&J GULF EQUIPMENT MANUFACTURING L.L.C
Job Costing Sheet
REF NO: JOB-20260422-869FB5
CUSTOMER NAME |  |  | DATE |  | 2026-04-22 | [5 empty] | ENQUIRY No
CUSTOMER CODE |  |  | ATTENTION OF | [7 empty] | JOB NO. |  | JOB-20260422-869FB5
EMAIL |  |  | CONTACT NO: | [7 empty] | JORL DATE:
PROJECT PACKAGE DETAILS |  |  | MODULE WORK
CUSTOMER P.O. Ref :
SALES EMPOLOYEE CODE
NETSUITE INVOICE NO: |  |  | NETSUITE AGEING REPORT:
PENDING PAYMENT
[5 empty] | COST AT OFFER ACCEPTANCE AS PER ESTIMATION | [5 empty] | ACTUAL MANUFACTURING COST
Sr No | Item Description |  |  |  | Qty | Unit | Manhours | Unit cost | Total cost | Remarks | Qty | Unit | Unit cost | Total cost | Remarks
Structural Work
1 | Design, Drafting & Drawing Charges |  |  |  |  | lot
1.1 | Gaps in customer design |  |  |  |  | lot
2 | BOM/BOQ Preparation |  |  |  |  | lot
2.1 | Changes in BOM due to Design change |  |  |  |  | lot
3 | Technical recommendations to customer |  |  |  |  | lot
4 | Gaps in our estimation |  |  |  |  | lot
5 | Material Cost
5.1 | Structural Steel Material |  |  |  | 1842.6 | Kg |  | 3.5
5.2 | M20x90 Long Bolts HEX HD |  |  |  | 72 | Nos |  | 12.5
5.3 | Paint Material |  |  |  | 27.8 | litres |  | 21
6 | Material Inspection Charges |  |  |  |  | lot
7 | Labour & Fabrication Cost
7.1 | Structural Welding Labour |  |  |  |  | Hrs | 148 | 45
7.2 | Structural Fabrication Labour |  |  |  |  | Hrs | 296 | 45
7.3 | Hydrotesting |  |  |  |  | Inch Dia |  | 11
7.4 | Machining 8 labour hours per day for 4 days |  |  |  |  | Kg |  | 9.5
8 | Consumables |  |  |  |  | lot
9 | Subcontractor Costing
9.1 | Machining & Threading |  |  |  |  | Pcs |  | 65
10 | Testing & Quality Control
10.1 | 10% MPI/DPT |  |  |  |  | Visits |  | 600
11 | Surface Preparation & Coating
11.1 | Galvanizing Work |  |  |  |  | Kg |  | 2
11.2 | Blasting (185.0 Sq M) |  |  |  | 185 | SQM |  | 9
11.3 | Painting (185.0 Sq M) |  |  |  | 185 | SQM |  | 11
12 | Third-Party Inspection (TPI) |  |  |  |  | lot
13 | MPI / DPT Inspection (2 visits) |  |  |  | 2 | Visits |  | 600
14 | Packing and loading |  |  |  |  | Lot |  | 3000
16 | Insurance |  |  |  |  | lot
17 | QA/QC Documentation & NDT |  |  |  | 1 | Lot |  | 3000
18 | Packing & Loading |  |  |  | 1 | Lot |  | 3000
20 | Contingency Fund |  |  |  |  | lot
21 | Taxes & Duties |  |  |  |  | lot
22 | Warranty & Guarantee Costs |  |  |  |  | lot
23 | Project Management Fees |  |  |  |  | lot
24 | Environmental Compliance Costs |  |  |  |  | lot
25 | Training & Certification |  |  |  |  | lot
26 | Marketing & Sales Costs |  |  |  |  | lot
Total cost |  | 40076 |  |  | ESTIMATION ENGR. |  |  | Sachin Ahire |  |  | PLANNING ENGR. |  |  | Sachin Ahire
19.Overheads |  | 4809.12 |  |  | MANAGER: |  |  | Subash Valrani |  |  | MANAGER: |  |  | Subash Valrani
GRAND TOTAL |  | 44885.12 | [8 empty] | ACCOUNTANT: |  |  | Zeeshan
Selling Price |  | 60167.72
Net Profit |  | 15282.6
25.4%

## RATES & CONFIG
RATE CONFIGURATION SNAPSHOT
Parameter | Value | Unit
material_rate_per_kg | 3.5 | AED/kg
bolt_rate_per_nos | 12.5
bolt_rate_m16_per_nos | 8.5
paint_material_rate_per_litre | 21
paint_litres_per_kg | 0.01538
welding_hourly_rate | 45 | AED/hr
welding_factor_hr_per_kg | 0.02051
fabrication_hourly_rate | 45 | AED/hr
fabrication_factor_hr_per_kg | 0.04102
blasting_rate_per_m2 | 9
painting_rate_per_m2 | 11
surface_area_factor_m2_per_kg | 0.0256
consumables_rate_per_kg_steel | 0.6855
mpi_rate_per_visit | 600
mpi_kg_per_visit | 800
galvanizing_rate_per_kg | 2
qaqc_fixed | 3000
packing_fixed | 3000
overhead_percentage | 12 | %
profit_margin_on_sell_pct | 25.4
steel_density_kg_m3 | 7850
fabrication_rate_per_kg | 6
manhour_factor_hr_per_kg | 0.15
welding_time_per_m_hr | 0.8
consumable_factor_kg_per_m | 0.12
consumable_unit_rate | 15
cutting_rate_per_cut | 25
surface_treatment_rate_per_m2 | 55 | AED/m2
profit_margin_percentage | 15 | %
weld_length_per_joint_mm | 150
structural_steel_aed_per_kg | 5.5
stainless_steel_aed_per_kg | 22
bolt_m16_aed_per_piece | 2.5
bolt_m20_aed_per_piece | 3.8
bolt_m24_aed_per_piece | 5.2
consumables_percentage_of_steel | 3.5
paint_2pack_epoxy_aed_per_litre | 85
paint_coverage_factor_m2_per_litre | 6.67
labour_hourly_rate_aed | 35
welding_manhours_per_kg | 0.35
fabrication_manhours_per_kg | 0.28
fitting_manhours_per_kg | 0.18
grinding_manhours_per_kg | 0.07
galvanizing_aed_per_kg | 3.2
blasting_sa25_aed_per_m2 | 12
painting_aed_per_m2 | 18
transport_percentage_of_total | 2.5
transport_minimum_aed | 1500
standard_schedule_weeks | 4
rush_surcharge_percentage | 20

## AUDIT TRAIL
CALCULATION AUDIT TRAIL
Step / Item | Status | Details
CS-2620-001 | weight_ok | {'weight_kg': 0.0}
CS-2620-001 | weight_ok | {'weight_kg': 0.0}
CS-2620-001 | weight_ok | {'weight_kg': 0.0}
CS-2620-001 | weight_ok | {'weight_kg': 7.536}
CS-2620-002 | weight_ok | {'weight_kg': 0.0}
CS-2620-002 | weight_ok | {'weight_kg': 0.0}
CS-2620-002 | weight_ok | {'weight_kg': 7.536}
CS-2620-003 | weight_ok | {'weight_kg': 0.0}
CS-2620-003 | weight_ok | {'weight_kg': 0.0}
CS-2620-003 | weight_ok | {'weight_kg': 7.536}
CS-2620-004 | weight_ok | {'weight_kg': 0.0}
CS-2620-004 | weight_ok | {'weight_kg': 0.0}
CS-2620-004 | weight_ok | {'weight_kg': 7.536}
CS-2620-005 | weight_ok | {'weight_kg': 0.0}
CS-2620-005 | weight_ok | {'weight_kg': 0.0}
CS-2620-005 | weight_ok | {'weight_kg': 7.536}
CS-2620-006 | weight_ok | {'weight_kg': 0.0}
CS-2620-006 | weight_ok | {'weight_kg': 0.0}
CS-2620-006 | weight_ok | {'weight_kg': 7.536}
CS-2620-007 | weight_ok | {'weight_kg': 0.0}
CS-2620-007 | weight_ok | {'weight_kg': 0.0}
CS-2620-007 | weight_ok | {'weight_kg': 7.536}
C&J_10_step_aggregate | ok | {'total_steel_kg': 1842.6, 'step1_steel': 6449.1, 'step2_bolts': '72 nos × 12.5 = 900.0', 'step3_paint': '27.8 L × 21.0 = 583.8', 'step4_welding': '148.0 hrs × 45.0 = 6660.0', 'step5_fabrication': '296.0 hrs × 45.0 = 13320.0', 'step6_blasting': '185.0 m² × 9.0 = 1665.0', 'step6_painting': '185.0 m² × 11.0 = 2035.0', 'step7_consumables': 1263.1, 'step8_mpi': '2 visits × 600.0 = 1200.0', 'step9_fixed': 'QA/QC 3000.0 + Packing 3000.0', 'total_direct': 40076.0, 'overhead': '12.0% = 4809.12', 'grand_total': 44885.12, 'selling_price': 60167.72, 'net_profit': 15282.6}