## 142676- Structure Frame
C&J GULF EQUIPMENT MANUFACTURING L.L.C
Job Costing Sheet
REF NO: CNJ/142676/01/2025
CUSTOMER NAME |  | Descon Engineering |  | DATE |  | 2025-01-29 | [5 empty] | ENQUIRY No |  | 142676
CUSTOMER CODE |  |  |  | ATTENTION OF |  | Mr. Harun Khan | [5 empty] | JOB NO.
EMAIL |  |  |  | CONTACT NO: |  | 971566529515 | [5 empty] | JORL DATE:
PROJECT PACKAGE DETAILS |  | PIPING |  | MODULE WORK |  | X |  |  | SKID MOUNTED PACKAGE |  |  |  |  | CEMENT LINING
CUSTOMER P.O. Ref :
SALES EMPOLOYEE CODE
NETSUITE INVOICE NO: |  |  |  | NETSUITE AGEING REPORT:
PENDING PAYMENT
[6 empty] | COST AT OFFER ACCEPTANCE AS PER ESTIMATION | [5 empty] | ACTUAL MANUFACTURING COST
Sr No | Item Description |  |  |  |  | Qty | Unit | Manhours | Unit cost | Total cost | Remarks | Qty | Unit | Unit cost | Total cost | Remarks
Structural Work
1 | Design, Drafting & Drawing Charges |  |  |  |  | 0 | lot |  |  | 0
1.1 | Gaps in customer design |  |  |  |  | 0 | lot |  |  | 0
2 | BOM/BOQ Preparation |  |  |  |  | 0 | lot |  |  | 0
2.1 | Changes in BOM due to Design change |  |  |  |  | 0 | lot |  |  | 0
3 | Technical recommendations to customer |  |  |  |  | 0 | lot |  |  | 0
4 | Gaps in our estimation |  |  |  |  | 0 | lot |  |  | 0
5 | Material Cost | Pipe 3'' Pipe Sch 40 thk 105 mm Lg. | Pipe 3'' Pipe Sch 40 thk 105 mm Lg. | Pipe 3'' Pipe Sch 40 thk 105 mm Lg. | [5 empty] | 0
5.1 | Structural Steel Material |  |  |  |  | 7802.27 | Kg |  | 4 | 31209.08
5.2 | M20X90 Long Bolts HEX HD & Nut to BS 4190 Gr.8.8 |  |  |  |  | 30 | Nos |  | 12.5 | 375
5.3 | Paint Material |  |  |  |  | 120 | litres |  | 21 | 2520
6 | Material Inspection Charges |  |  |  |  | 0 | lot |  |  | 0
0
7 | Labour & Fabrication Cost | [8 empty] | 0
7.1 | Structural Welding considering 16 labor hours per day for 10 Days | Pipe 3'' Pipe Sch 40 thk 105 mm Lg. | Pipe 3'' Pipe Sch 40 thk 105 mm Lg. | Pipe 3'' Pipe Sch 40 thk 105 mm Lg. |  | 7802.27 | Kg | 160 | 10.5 | 1680 |  | 2 Welder |  |  |  |  | 5111.1111
7.2 | Structuralt Fabrication considering 32 labor hours per day for 10 Days | Pipe 3'' Pipe Sch 40 thk 105 mm Lg. | Pipe 3'' Pipe Sch 40 thk 105 mm Lg. | Pipe 3'' Pipe Sch 40 thk 105 mm Lg. |  | 7802.27 | Kg | 320 | 9.5 | 3040 |  | 2 Fabricator 2 Helper |  |  |  |  | 10222.2222
7.3 | Hydrotesting | [5 empty] | Inch Dia |  | 11 | 0 | [6 empty] | 0
7.4 | Machining 8 labour hours per day for 4 days | [5 empty] | Kg |  | 9.5 | 0 |  | 1 Machinist
8 | Consumables |  |  |  |  | 1 | lot |  | 5348.31 | 5348.31
9 | Subcontractor Costing | [8 empty] | 0
9.1 | Machining & Threading |  |  |  |  | 0 | Pcs |  | 65 | 0
10 | Testing & Quality Control | [8 empty] | 0
10.1 | 10% MPI/DPT |  |  |  |  | 10 | Visits |  | 600 | 6000
11 | Surface Preparation & Coating | [8 empty] | 0
11.1 | Galvanizing Work |  |  |  |  | 0 | Kg |  | 2000 | 0 | [6 empty] | 1441.1028
11.2 | Blasting (13.3 Sq M per hour) |  |  |  |  | 200 | SQM | 45.1128 | 9 | 1800 |  | 1 Blaster 1 Helper |  |  |  |  | 2882.2055
11.3 | Painting(6.65 Sq M per hour for 2 coat paint system) |  |  |  |  | 200 | SQM | 90.2256 | 11 | 2200 |  | 1 Painter 1 Helper
12 | Third-Party Inspection (TPI) |  |  |  |  | 0 | lot |  |  | 0
13 | QA/QC Documentation & Certification |  |  |  |  | 1 | lot |  | 3000 | 3000
14 | Packing and loading |  |  |  |  | 1 | Lot |  | 3000 | 3000
16 | Insurance |  |  |  |  | 0 | lot |  |  | 0
17 | Permits, Licenses & Regulatory Fees |  |  |  |  | 0 | Nos |  |  | 0
18 | Equipment Rental & Maintenance |  |  |  |  | 0 | lot |  |  | 0
20 | Contingency Fund |  |  |  |  | 0 | lot |  |  | 0
21 | Taxes & Duties |  |  |  |  | 0 | lot |  |  | 0
22 | Warranty & Guarantee Costs |  |  |  |  | 0 | lot |  |  | 0
23 | Project Management Fees |  |  |  |  | 0 | lot |  |  | 0
24 | Environmental Compliance Costs |  |  |  |  | 0 | lot |  |  | 0
25 | Training & Certification |  |  |  |  | 0 | lot |  |  | 0
26 | Marketing & Sales Costs |  |  |  |  | 0 | lot |  |  | 0 | [6 empty] | 19656.6416
Total cost |  |  | 60172.39 |  |  | ESTIMATION ENGR. |  |  | Sachin Ahire |  |  | PLANNING ENGR. |  |  | Sachin Ahire
19.Overheads |  |  | 19656.6416 |  |  | MANAGER: |  |  | Subash Valrani |  |  | MANAGER: |  |  | Subash Valrani
GRAND TOTAL |  |  | 79829.0316 | [8 empty] | ACCOUNTANT: |  |  | Zeeshan
Selling Price |  |  | 106966.2
Net Profit |  |  | 27137.1684
25.37%
46793.81